## RFI Register
HARBOR BUILD ¦ PROJECT BETA 2026 RFI REGISTER | HARBOR BUILD ¦ PROJECT BETA 2026 RFI REGISTER | HARBOR BUILD ¦ PROJECT BETA 2026 RFI REGISTER | HARBOR BUILD ¦ PROJECT BETA 2026 RFI REGISTER | HARBOR BUILD ¦ PROJECT BETA 2026 RFI REGISTER | HARBOR BUILD ¦ PROJECT BETA 2026 RFI REGISTER | HARBOR BUILD ¦ PROJECT BETA 2026 RFI REGISTER | HARBOR BUILD ¦ PROJECT BETA 2026 RFI REGISTER | HARBOR BUILD ¦ PROJECT BETA 2026 RFI REGISTER | HARBOR BUILD ¦ PROJECT BETA 2026 RFI REGISTER
Portfolio | Harbor Build / Project Beta 2026
Status date | 2026-07-29
Purpose | Open RFI coordination and aging control
Cross-project note | Project Alpha / CO-014 is reference only; no Alpha cost is assigned to Beta.
RFI | Subject | Discipline | Issued | Requested by | Status | Age days | Priority | Response / action | Close target
BETA-006 | Structural opening at Grid B-4 | Structural / MEP | 2026-07-27 | 2026-08-03 | Open - priority | 2 | High | Confirm opening location; no field core drilling. | 2026-08-04
BETA-009 | Facade anchor spacing | Facade / Structural | 2026-07-25 | 2026-08-05 | Open | 4 | High | Confirm maximum horizontal anchor adjustment. | 2026-08-06
BETA-004 | Roof drain overflow routing | Plumbing / Architectural | 2026-07-17 | 2026-07-28 | Response received - closeout pending | 12 | Medium | Link returned sketch then close register entry. | 2026-07-30
BETA-002 | Service corridor ceiling access | Architectural | 2026-07-11 | 2026-07-22 | Closed | 18 | Low | Incorporated in coordination drawing. | 2026-07-24

## Control Summary
PROJECT BETA ¦ RFI CONTROL SUMMARY | PROJECT BETA ¦ RFI CONTROL SUMMARY | PROJECT BETA ¦ RFI CONTROL SUMMARY | PROJECT BETA ¦ RFI CONTROL SUMMARY | PROJECT BETA ¦ RFI CONTROL SUMMARY | PROJECT BETA ¦ RFI CONTROL SUMMARY
Metric | Value |  | Control note
Open RFIs | 2 |  | Decision focus | BETA-006 and BETA-009 need written direction before planned releases.
Priority open RFIs | 2 |  | Portfolio separation | Alpha/CO-014 is context only; Beta cost is not represented in this workbook.
Average age - open | 3 |  | As-of date | 2026-07-29
Overdue requested-by date | 0 |  | Register basis | Formula-driven values source the RFI Register sheet.