## Register
Project Beta Submittal Register | [7 empty] | Status Summary
Harbor Build ¦ Status date: 2026-07-29 ¦ Synthetic internal record | [7 empty] | Total open | 6
[8 empty] | Under review | 2
Submittal ID | Spec Section | Package | Received | Current Status | Next Review | Open Coordination Item | Review Lead | Approved as noted | 1
BETA-033000-02 | 03 30 00 | Concrete mix design | 2026-07-24 | Revise and Resubmit | 2026-08-01 | Need aggregate gradation and curing cross-reference | Project Controls | Resubmit | 1
BETA-072100-04 | 07 21 00 | Mineral wool insulation | 2026-07-27 | Approved as Noted | 2026-08-03 | Confirm perimeter-facing transition detail | Envelope Lead
BETA-055000-01 | 05 50 00 | Metal fabrications | 2026-07-28 | Under Review | 2026-08-02 | Coordinate embeds with concrete package | Structural Lead
BETA-078400-03 | 07 84 00 | Firestopping systems | 2026-07-29 | Under Review | 2026-08-04 | Verify listed system at mixed-material joints | Life Safety Lead
BETA-079200-01 | 07 92 00 | Joint sealants | 2026-07-29 | Received | 2026-08-05 | Initial completeness screening scheduled | Envelope Lead
BETA-096500-02 | 09 65 00 | Resilient flooring sample | 2026-07-29 | Received | 2026-08-06 | Color and maintenance data to be reviewed | Interiors Lead