## Approval Tracker
Project Beta Material Approval Tracker | [7 empty] | Metric | Formula
Harbor Build ¦ Review health snapshot as of 2026-07-29 | [7 empty] | Packages | 5
[8 empty] | Avg completion | 54%
Submittal ID | Material Package | Received | Last Action | Disposition | Review Complete | Constraint / Note | Target Date | Approval rate | 20%
BETA-033000-02 | Concrete | 2026-07-24 | 2026-07-29 | Revise and Resubmit | 65% | Gradation; curing statement | 2026-08-01 | Action required | 3
BETA-072100-04 | Insulation | 2026-07-27 | 2026-07-29 | Approved as Noted | 90% | Perimeter facing transition | 2026-08-03
BETA-055000-01 | Metal fabrications | 2026-07-28 |  | Under Review | 50% | Embed coordination | 2026-08-02
BETA-078400-03 | Firestopping | 2026-07-29 |  | Under Review | 45% | Listed system selection | 2026-08-04
BETA-079200-01 | Joint sealants | 2026-07-29 |  | Received | 20% | Completeness check | 2026-08-05