# Study Alpha Field Research Plan

Seed plan - moderated usability research

Beacon Field Research

2026-07-13

# Study Alpha Field Research Plan

Beacon Field Research | Study Alpha | 2026-07-13 | session UX-184 | n=24

## Decision frame

Study Alpha tests whether a revised workflow can be understood, navigated, and recovered by a mixed-accessibility participant set. The study is exploratory; it does not establish prevalence or product readiness.

## Objectives

- Identify comprehension barriers before task start.

- Observe navigation and recovery patterns through representative tasks.

- Surface accessibility needs that change the recommended design response.

## Method and sample

Twenty-four synthetic participant codes will complete 60-minute moderated remote sessions. Sampling spans experience bands and assistive-technology familiarity. Session UX-184 is the calibration session on 2026-07-13; S2 and S3 are synthetic shorthand cohorts, not names.

## Session flow

Consent confirmation (5 min); context and warm-up (5 min); task scenarios (32 min); accessibility probes (10 min); reflection and close (8 min). Observers remain muted, use the evidence log, and do not contact participants.

## Outputs

A coded observation set, severity-calibrated opportunity list, accessibility evidence, and an analysis handoff brief. Findings will distinguish observed behavior, participant interpretation, and facilitator inference.

## Success signals

At least 20 analyzable sessions; consistent consent confirmation; remote fallback available; and a traceable handoff linking each claim to coded evidence.

Synthetic research artifact; participant codes only; no real PII, recordings, faces, voices, credentials, or copied content.